## Gantt
ID | Phase | Task | Model | Start | End | Work days | Depends on | % Complete | Status | Done days | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08
T0.1 | P0 | Overview & design brief | human | 2026-09-21 | 2026-09-23 | 3 |  | 100%
T0.2 | P0 | Detailed specs + adversarial review | human | 2026-09-24 | 2026-09-25 | 3 | T0.1 | 100%
T0.3 | P0 | Gantt, review deck, OKRs | human | 2026-09-26 | 2026-09-26 | 1 | T0.2 | 100%
T0.4 | P0 | Owner review & sign-off of plan | human | 2026-09-28 | 2026-09-30 | 3 | T0.3 | 100%
T1.1 | P1 | Repo scaffold: cargo workspace, icp.yaml, toolch… | haiku-4.5 | 2026-10-01 | 2026-10-01 | 1 | T0.4 | 100%
T1.2 | P1 | sc-types shared crate (types, ApiError, limits) | sonnet-5 | 2026-10-02 | 2026-10-05 | 2 | T1.1 | 100%
T1.3 | P1 | Local verification & deploy harness (verify-loca… | haiku-4.5 | 2026-10-02 | 2026-10-05 | 2 | T1.1 | 100%
T1.4 | P1 | PocketIC harness with ICP ledger + CMC wasms | sonnet-5 | 2026-10-02 | 2026-10-05 | 2 | T1.1 | 100%
SP-7 | P1 | Spike: Galaxy Zoo JWST (CEERS) labels, licence, … | sonnet-5 | 2026-10-06 | 2026-10-06 | 1 | T0.4 | 100%
T1.5 | P1 | JWST subject selection + gold (DJA v7 catalogs, … | sonnet-5 | 2026-10-07 | 2026-10-13 | 5 | SP-7 | 0%
T1.7 | P1 | Render dossiers (cutouts, RGB, dossier.json) + R… | sonnet-5 | 2026-10-14 | 2026-10-20 | 5 | T1.5 | 0%
SP-1 | P1 | Spike: CMC + ICRC-2 memo behaviour | sonnet-5 | 2026-10-06 | 2026-10-06 | 1 | T1.4 | 100%
SP-3 | P1 | Spike: frozen canister query behaviour | haiku-4.5 | 2026-10-06 | 2026-10-06 | 1 | T1.4 | 100%
SP-4 | P1 | Spike: canister_info cost/latency | haiku-4.5 | 2026-10-07 | 2026-10-07 | 1 | T1.4 | 100%
SP-6 | P1 | Spike: ckETH helper subaccount deposit + minimum | sonnet-5 | 2026-10-07 | 2026-10-07 | 1 | T1.4 | 100%
SP-2 | P1 | Spike: OISY approve w/ spender subaccount | sonnet-5 | 2026-10-08 | 2026-10-08 | 1 | T0.4 | 100%
T1.8 | P1 | Test infra: coverage, fuzz, Playwright+axe, bot-… | sonnet-5 | 2026-10-08 | 2026-10-12 | 3 | T1.3,T1.4 | 0%
T2.1 | P2 | platform skeleton: config/admin, memory map, tim… | sonnet-5 | 2026-10-09 | 2026-10-12 | 2 | T1.2 | 0%
T2.2 | P2 | Registry & factory: register/install/verify/upgr… | opus-5.5 (high) | 2026-10-13 | 2026-10-16 | 4 | T2.1,SP-4 | 0%
T2.3 | P2 | Catalog: subjects, protocol, leases, seen-set, g… | sonnet-5 | 2026-10-13 | 2026-10-16 | 4 | T2.1 | 0%
T2.4 | P2 | Scoring: validation, gold, tallies, retirement, … | opus-5.5 (high) | 2026-10-19 | 2026-10-22 | 4 | T2.3 | 0%
T2.5 | P2 | Event log + per-AAA index + activity query | sonnet-5 | 2026-10-19 | 2026-10-20 | 2 | T2.1 | 0%
T2.6 | P2 | Public queries: stats, protocol, aaa_by_owner, a… | haiku-4.5 | 2026-10-21 | 2026-10-21 | 1 | T2.2 | 0%
T2.8 | P2 | Submitter security: strict provenance, operator … | opus-5.5 (high) | 2026-10-21 | 2026-10-23 | 3 | T2.2 | 0%
T2.7 | P2 | Platform PocketIC tests (02 §11 #1-3) | sonnet-5 | 2026-10-23 | 2026-10-26 | 2 | T2.4,T1.4 | 0%
T3.1 | P3 | AAA skeleton: roles, operators, config, inspect_… | sonnet-5 | 2026-10-23 | 2026-10-26 | 2 | T1.2 | 0%
T3.2 | P3 | AAA forwarding w/ fees, retries, idempotency, lo… | opus-5.5 (high) | 2026-10-27 | 2026-10-29 | 3 | T3.1,T2.4 | 0%
T3.3 | P3 | AAA repository records + queries + credits copy | haiku-4.5 | 2026-10-30 | 2026-11-02 | 2 | T3.2 | 0%
T3.4 | P3 | AAA timers: burn EMA, heartbeat, credits sync, a… | sonnet-5 | 2026-11-03 | 2026-11-04 | 2 | T3.3 | 0%
T3.5 | P3 | get_api_doc + wasm size budget ≤1.5 MiB gz | haiku-4.5 | 2026-10-30 | 2026-10-30 | 1 | T3.2 | 0%
T3.6 | P3 | AAA PocketIC tests (03 §8) | sonnet-5 | 2026-11-05 | 2026-11-06 | 2 | T3.4 | 0%
T3.8 | P3 | Local seed script + dev loop (tools/seed-local) | haiku-4.5 | 2026-10-30 | 2026-10-30 | 1 | T2.2,T3.2,T1.7,T1.8 | 0%
T3.7 | P3 | Operator skill + JWST protocol primer + analyze.… | opus-5.5 (high) | 2026-11-02 | 2026-11-05 | 4 | T3.5,T1.7 | 0%
T3.9 | P3 | Headless runner recipe + practice.py self-eval | haiku-4.5 | 2026-11-06 | 2026-11-06 | 1 | T3.7 | 0%
T4.3 | P4 | Progression: XP, reputation, tiers, badges, lead… | sonnet-5 | 2026-11-02 | 2026-11-05 | 4 | T2.5,T2.7 | 0%
T4.1 | P4 | Discoveries: flagging, rate limit, public IDs | sonnet-5 | 2026-11-06 | 2026-11-09 | 2 | T2.4 | 0%
T4.9 | P4 | First-claim rule: sky claim index + corroboratio… | opus-5.5 (high) | 2026-11-10 | 2026-11-11 | 2 | T4.1 | 0%
T4.2 | P4 | Review assignment: eligibility, blind, leases, h… | opus-5.5 (high) | 2026-11-10 | 2026-11-12 | 3 | T4.1,T4.3 | 0%
T4.4 | P4 | evaluate(), atomic resolution, starvation rule | opus-5.5 (high) | 2026-11-13 | 2026-11-17 | 3 | T4.2 | 0%
T4.5 | P4 | Citations + certification tree + get_citation | opus-5.5 (high) | 2026-11-18 | 2026-11-20 | 3 | T4.4 | 0%
T4.6 | P4 | Visibility rules & public discovery queries | sonnet-5 | 2026-11-23 | 2026-11-24 | 2 | T4.5 | 0%
T4.7 | P4 | Honeypot seeding (120 specs) | haiku-4.5 | 2026-11-13 | 2026-11-13 | 1 | T4.2,T1.7 | 0%
T4.10 | P4 | Admin read APIs + audit log (platform) | haiku-4.5 | 2026-11-25 | 2026-11-30 | 2 | T4.6 | 0%
T4.11 | P4 | Name blocklist, admin_rename_aaa, house AAAs | haiku-4.5 | 2026-12-01 | 2026-12-01 | 1 | T4.10 | 0%
T4.8 | P4 | Review/credits tests + proptests (02 §11 #4-9) | sonnet-5 | 2026-11-25 | 2026-12-01 | 3 | T4.6,T4.9 | 0%
T5.1 | P5 | payments skeleton: config, journal, guards, admin | sonnet-5 | 2026-11-10 | 2026-11-11 | 2 | T1.2,SP-1 | 0%
T5.2 | P5 | CMC integration, XDR cache, quotes, deposit acco… | sonnet-5 | 2026-11-12 | 2026-11-13 | 2 | T5.1 | 0%
T5.3 | P5 | Spawn saga (wallet + deposit) + resume timer | opus-5.5 (high) | 2026-11-16 | 2026-11-19 | 4 | T5.2,T2.2 | 0%
T5.4 | P5 | One-time top-up (wallet + deposit sweep) | sonnet-5 | 2026-11-20 | 2026-11-23 | 2 | T5.2 | 0%
T5.5 | P5 | Auto top-up mandates, rolling 30-day cap | sonnet-5 | 2026-11-24 | 2026-11-30 | 3 | T5.4,T3.4 | 0%
T5.6 | P5 | Payments PocketIC tests — ICP paths (04 §5) | sonnet-5 | 2026-12-01 | 2026-12-03 | 3 | T5.3,T5.5 | 0%
T5.8 | P5 | XRC rates, fuel treasury guard rails + auto inta… | opus-5.5 (high) | 2026-12-02 | 2026-12-07 | 4 | T5.2 | 0%
T5.12 | P5 | stripe_credit endpoint (flag-gated, mock-relay t… | haiku-4.5 | 2026-12-08 | 2026-12-09 | 2 | T5.8 | 0%
T5.9 | P5 | ckBTC fuel-pack deposits (address, update_balanc… | opus-5.5 (high) | 2026-12-08 | 2026-12-10 | 3 | T5.8 | 0%
T5.10 | P5 | ckETH fuel-pack deposits | sonnet-5 | 2026-12-08 | 2026-12-09 | 2 | T5.8,SP-6 | 0%
T5.13 | P5 | Non-ICP payment tests (04 §6.7) | sonnet-5 | 2026-12-11 | 2026-12-14 | 2 | T5.9,T5.10,T5.12 | 0%
T5.15 | P5 | Payments admin APIs + audit log | haiku-4.5 | 2026-12-15 | 2026-12-15 | 1 | T5.13 | 0%
T5.16 | P5 | Feature flags + invite codes (sponsored spawn) | sonnet-5 | 2026-12-10 | 2026-12-11 | 2 | T5.3 | 0%
T5.17 | P5 | treasury canister: owner-funded reserve, cycles … | opus-5.5 (high) | 2026-12-11 | 2026-12-15 | 3 | T2.1,T1.4 | 0%
T5.18 | P5 | treasury PocketIC tests (ICP ledger + CMC, no NN… | sonnet-5 | 2026-12-16 | 2026-12-16 | 1 | T5.17 | 0%
T5.7 | P5 | Internal payments security review | opus-5.5 (high) | 2026-12-15 | 2026-12-16 | 2 | T5.6,T5.13,T5.16 | 0%
T6.1 | P6 | App scaffold: routing, bindgen, II auth, ic_env,… | sonnet-5 | 2026-12-16 | 2026-12-18 | 3 | T1.1 | 0%
T6.3 | P6 | Landing, Discovery Museum feed, Discovery detail… | sonnet-5 | 2026-12-21 | 2026-12-29 | 5 | T6.1 | 0%
T6.4 | P6 | AAA profile + Leaderboard | haiku-4.5 | 2026-12-30 | 2027-01-05 | 3 | T6.3 | 0%
T6.5 | P6 | Payment component (wallet + deposit) | sonnet-5 | 2026-12-21 | 2026-12-28 | 4 | T6.1,SP-2,T5.4 | 0%
T6.6 | P6 | Spawn flow | haiku-4.5 | 2026-12-29 | 2026-12-30 | 2 | T6.5,T5.3 | 0%
T6.7 | P6 | Owner dashboard | sonnet-5 | 2026-12-21 | 2026-12-28 | 4 | T6.1,T3.3,T4.6 | 0%
T6.8 | P6 | Connect your agent + Activity & records | haiku-4.5 | 2026-12-29 | 2027-01-04 | 3 | T6.7 | 0%
T6.9 | P6 | Fuel & billing + auto top-up | haiku-4.5 | 2027-01-04 | 2027-01-06 | 3 | T6.5,T5.5 | 0%
T6.11 | P6 | BTC & ETH methods + feature-flag gating (card hi… | sonnet-5 | 2027-01-05 | 2027-01-08 | 4 | T6.5,T5.9,T5.10 | 0%
T6.12 | P6 | Admin console (8 screens) | sonnet-5 | 2027-01-06 | 2027-01-12 | 5 | T6.1,T4.10,T5.15 | 0%
T6.13 | P6 | Firebase analytics + consent + event taxonomy + … | haiku-4.5 | 2027-01-07 | 2027-01-08 | 2 | T6.1 | 0%
T6.14 | P6 | About/legal/practice pages, invite spawn UI, adm… | haiku-4.5 | 2027-01-13 | 2027-01-15 | 3 | T6.12,T5.16,T5.18 | 0%
T6.10 | P6 | States, accessibility, Playwright smoke | sonnet-5 | 2027-01-18 | 2027-01-20 | 3 | T6.4,T6.6,T6.8,T6.9,T6.11,T6.12,T6.13,T6.14 | 0%
T7.1 | P7 | Upgrade tests for all canisters | sonnet-5 | 2027-01-11 | 2027-01-12 | 2 | T4.8,T5.6 | 0%
T7.2 | P7 | Load test: 200 AAAs × 100 tasks | sonnet-5 | 2027-01-13 | 2027-01-14 | 2 | T7.1 | 0%
T7.3 | P7 | Cycle cost measurement & fee retune | sonnet-5 | 2027-01-15 | 2027-01-18 | 2 | T7.2 | 0%
T7.4 | P7 | Reproducible AAA build + manual upgrade docs | sonnet-5 | 2027-01-11 | 2027-01-12 | 2 | T3.6,T5.7 | 0%
T7.7 | P7 | Prompt-injection test with reference agent | opus-5.5 (high) | 2027-01-13 | 2027-01-13 | 1 | T3.7,T4.7 | 0%
T7.9 | P7 | Traceability audit + coverage gates to thresholds | haiku-4.5 | 2027-01-14 | 2027-01-15 | 2 | T7.1 | 0%
T7.10 | P7 | Practice set + open data release tooling | haiku-4.5 | 2027-01-18 | 2027-01-19 | 2 | T1.7,T4.8 | 0%
T7.5 | P7 | External security review (payments + platform) | human | 2026-12-17 | 2026-12-23 | 5 | T5.7,T4.8 | 0%
T7.6 | P7 | Fix security findings | opus-5.5 (high) | 2027-01-19 | 2027-01-21 | 3 | T7.5 | 0%
T8.1 | P8 | Staging deploy, deploy workflow, snapshots, cycl… | sonnet-5 | 2027-01-20 | 2027-01-21 | 2 | T7.1 | 0%
T8.2 | P8 | Upload subjects/protocol/honeypots to staging | haiku-4.5 | 2027-01-22 | 2027-01-22 | 1 | T8.1,T7.6 | 0%
T8.5 | P8 | Fund prod treasury with ICP float (10–20 ICP) + … | human | 2027-02-10 | 2027-02-10 | 1 | T8.6 | 0%
T8.3 | P8 | Closed beta (10-20 owners) | human | 2027-01-25 | 2027-02-05 | 10 | T8.2,T6.10 | 0%
T8.4 | P8 | Beta fixes & tuning | sonnet-5 | 2027-01-25 | 2027-02-05 | 10 | T8.2,T6.10 | 0%
T8.6 | P8 | Production deploy, II metadata, treasury watch l… | sonnet-5 | 2027-02-08 | 2027-02-09 | 2 | T8.3,T8.4,T8.13 | 0%
T8.7 | P8 | Public launch | human | 2027-02-11 | 2027-02-11 | 1 | T8.6,T8.5,T9.5 | 0%
T9.1 | P9 | Import mockups (Claude Design), reconcile, desig… | sonnet-5 | 2027-01-22 | 2027-01-27 | 4 | T6.10 | 0%
T9.2 | P9 | Style public pages: landing, museum, discovery, … | sonnet-5 | 2027-01-28 | 2027-02-02 | 4 | T9.1 | 0%
T9.3 | P9 | Style owner flows: spawn, dashboard, connect age… | sonnet-5 | 2027-01-28 | 2027-02-02 | 4 | T9.1 | 0%
T9.4 | P9 | Style admin console + about/legal/practice pages | haiku-4.5 | 2027-02-03 | 2027-02-04 | 2 | T9.1 | 0%
T9.5 | P9 | Responsive/mobile pass, visual-regression baseli… | haiku-4.5 | 2027-02-05 | 2027-02-08 | 2 | T9.2,T9.3,T9.4 | 0%
T8.13 | P8 | Custom domain + II alternative origins | human | 2027-01-22 | 2027-01-22 | 1 | T8.1 | 0%
T8.12 | P8 | Firebase projects (staging/prod) + GA4 funnels &… | human | 2026-10-01 | 2026-10-01 | 1 | T0.4 | 0%
T8.8 | P8 | Compliance check for card & crypto fuel packs (r… | human | 2026-10-01 | 2026-10-07 | 5 | T0.4 | 0%
T8.9 | P8 | Enable BTC/ETH on production (card stays off) | human | 2027-02-10 | 2027-02-10 | 1 | T8.6,T8.8 | 0%

## Progress
Phase | Tasks | Work days | Done | In progress | Late | % complete (effort-weighted) | Start | End | Name
P0 | [6 empty] | 2026-09-21 | 2026-09-30 | Planning
P1 | [6 empty] | 2026-10-01 | 2026-10-20 | Foundations & spikes
P2 | [6 empty] | 2026-10-09 | 2026-10-26 | Platform core
P3 | [6 empty] | 2026-10-23 | 2026-11-06 | AAA canister & agent kit
P4 | [6 empty] | 2026-11-02 | 2026-12-01 | Review, consensus & credits
P5 | [6 empty] | 2026-11-10 | 2026-12-16 | Payments
P6 | [6 empty] | 2026-12-16 | 2027-01-20 | Frontend
P7 | [6 empty] | 2026-12-17 | 2027-01-21 | Hardening
P8 | [6 empty] | 2026-10-01 | 2027-02-11 | Beta & launch
P9 | [6 empty] | 2027-01-22 | 2027-02-08 | Design & polish (after function)
Overall | [6 empty] | 2026-09-21 | 2027-02-11
Edit only % Complete on the Gantt tab; everything else updates. Detail: docs/specs/10-tasks.md

## Milestones
Milestone | Gate task | Target date | Status
M1 Foundations + JWST data ready | T1.7
M2 Local alpha: agent classifies end-to-end | T3.8
M3 Review & credits complete | T4.8
M4 Payments complete | T5.7
M5 Frontend feature-complete (unstyled) | T6.10
M5b Design applied | T9.5
M6 Staging loaded & beta-ready backend | T8.2
M7 Public launch | T8.7